## Sheet1
SPRINT BACKLOG
NOT STARTED
IN PROGRESS
COMPLETED
[09/02/2015] - [20/02/2015]
Sprint 2 - TASK DESCRIPTION | Descripton (time in hrs) | Status | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri
1.2 - As a student I want to be able to give feedback on how informative the class was (and why)
Discuss input methods with students | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Create input method | 2 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Write and run unit tests | 2 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Acceptance testing | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
2.5 - As a lecturer I want to be able to select which module and lecturer the class belongs to immediately upon starting the app
Discuss nature of screen with lecturers | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Create input methods | 2 |  | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Acceptance testing | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
Write & run unit tests | 3 |  | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Update database schema | 2 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Create new PHP scripts | 5 |  | 5 | 5 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0
|  | Sprint 1: Ideal hours remaining: | 20 | 17 | 14 | 12 | 10 | 8 | 7 | 4 | 2 | 0
|  | Spring 1: Total Hours remaining | 20 | 11 | 7 | 5 | 4 | 4 | 4 | 4 | 2 | 0