## Sheet1
SPRINT BACKLOG
NOT STARTED
IN PROGRESS
COMPLETED
[19/01/2015] - [30/01/2015]
Sprint 1 - TASK DESCRIPTION | Descripton (time in hrs) | Status | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri
1.1 - As a student I want to be able to give feedback on how interesting the class was (and why)
Discuss input methods with students | 1 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Create input method | 2 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Acceptance testing | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
2.1 - As a lecturer I want to give students the option to select why a particular area/factor was bad or good (from a list of predefined statements)
Discuss nature of comments with lecturers | 1 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Create input method | 2 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Acceptance testing | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
Create PHP scripts | 5 |  | 5 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Create database | 5 |  | 5 | 5 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Link app to database via PHP | 8 |  | 8 | 8 | 5 | 5 | 3 | 2 | 0
Conduct Sprint Review | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
|  | Sprint 1: Ideal hours remaining: | 27 | 21 | 18 | 15 | 12 | 10 | 7 | 4 | 2 | 0
|  | Spring 1: Total Hours remaining | 27 | 20 | 13 | 9 | 6 | 5 | 3 | 3 | 1 | 0