## Sheet1
SPRINT BACKLOG
NOT STARTED
IN PROGRESS
COMPLETED
[23/02/2015] - [06/03/2015]
Sprint 3 - TASK DESCRIPTION | Descripton (time in hrs) | Status | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri
1.2 - As a student I want to be able to give feedback on how interactive the class was (and why)
Discuss input methods with students | 1 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Create input method | 2 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Write and run unit tests | 2 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Acceptance testing | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
1.4 - As a student I want to be able to give feedback on how intelligible the class was (and why)
Discuss input methods with students | 1 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Create input method | 2 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Write and run unit tests | 2 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Acceptance testing | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
1.5 - As a student I want to be able to give feedback on how innovative the class was (and why)
Discuss input methods with students | 1 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Create input method | 2 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Write and run unit tests | 2 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Acceptance testing | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
|  | Sprint 3: Ideal hours remaining: | 18 | 16 | 12 | 8 | 7 | 6 | 5 | 3 | 2 | 0
|  | Spring 3: Total Hours remaining | 18 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0