## Sheet1
SPRINT BACKLOG
NOT STARTED
IN PROGRESS
COMPLETED
[23/03/2015] - [03/04/2015]
Sprint 4 - TASK DESCRIPTION | Descripton (time in hrs) | Status | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri
1.2 - As a lecturer I want to be able to view the feedback(s) for individual classes
Discuss display methods and interface with lecturer(s) | 1 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Create basic website skeleton | 8 |  | 8 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Create 'My Feebacks' page | 3 |  | 3 | 3 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0
Create feedback display page | 8 |  | 8 | 8 | 8 | 8 | 8 | 6 | 4 | 3 | 1 | 0
Acceptance testing | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
|  | Sprint 4: Ideal hours remaining: | 21 | 18 | 15 | 12 | 10 | 8 | 6 | 4 | 2 | 0
|  | Spring 4: Total Hours remaining | 21 | 18 | 14 | 11 | 10 | 7 | 5 | 4 | 2 | 0